## Sheet1
Event Script Creating a day-by-day, hour-by-hour, minute-by-minute script not only helps draw out forgotten details during the planning process but is an essential tool during the actual event. The ability to prepare a comprehensive script is evidence that you have fully developed your action plan and left absolutely nothing to chance. It is a separate, more detailed document that will help you and your team execute your vision with accuracy and precision. Create your script in a project management or spreadsheet tool such as Microsoft Excel. This is a living document that will be continually updated throughout the planning process; using a spreadsheet makes it easy to insert rows in the middle of the schedule as additional tasks are identified during the planning process. The rows represent dates and times, and the columns contain at the very least the following: time, activity name, location, who is responsible, and additional details. I make sure that the spreadsheet is configured so that it can be easily reproduced and handed out to the entire team prior to the event so they can review it, ask questions, and mark all of the details they need to pay particular attention to. I carry my script with me everywhere I go, usually on a clipboard, so I can cross things off as they are completed, and pencil in my own notes and additions as needed. Inevitably, a participant or a sponsor will want to schedule an impromptu meeting; a quick glance at the script tells me that I have a free hour from 2:00 to 3:00 on Day 2. The script gives me the confidence to schedule a meeting during this time, knowing that I am not dropping the ball on something else.
EVENT SCRIPT
XYZ FALL CONFERENCE
| DATE/TIME | ACTIVITY | LOCATION | WHO | ADDITIONAL DETAILS
THE WEEK BEFORE | TUESDAY | Final Team Meeting
Distribute Script
Confirm arrival times and initial tasks
Review of emergency procedures
| WEDNESDAY | Gather, box, and label items to be shipped to venue:
Signs
Centerpieces and décor
Handouts
Team clothing and name badges
Programs
Conference totes and contents
Swag and promotional items
Badges or badge printing supplies
| THURSDAY | Speaker committee confirms details with each speaker
Speaker #1 contacted by (name)
Speaker #2 contacted by (name)
Speaker #3 contacted by (name)
| THURSDAY | Logistics committee confirms details with each vendor and service provider
Vendor #1 contacted by (name)
Vendor #2 contacted by (name)
Vendor #3 contacted by (name)
| THURSDAY | Logistics committee ships items to venue today
Box #1 containing:
Box #2 containing:
Box #3 containing:
| FRIDAY | Gather Supplies to be transported:
Contracts
BEO’s
Emergency Contacts
Attendance and exhibitor lists
Thank you notes
Payments for speaker or services
| FRIDAY | Final head counts to venue for each event:
9/14 Early Arrival Networking Event:
9/15 Day 1 Breakfast:
9/15 Day 1 Lunch:
9/15 Day 1 Afternoon Break:
9/15 Day 1 Dinner:
9/16 Day 2 Breakfast:
9/16 Day 2 Lunch:
9/16 Day 2 Afternoon Break:
9/16 Day 2 Dinner/Gala:
9/16 Day 2 After hours event:
9/17 Day 3 Breakfast:
2 DAYS BEFORE | MONDAY | Pack supplies for transport
Travel day
THE DAY BEFORE | TUESDAY
| 12:00 noon | Arrive at event site
Pre-con meeting with (name) and (name) from venue
Review BEO’s
Complete walkthrough of all spaces to confirm initial configurations
Confirm arrival of all shipped items
Setup Activities:
| 2:00 | A/V load-in begins
| 2:00 - 8:00 | Exhibitor load-in
Place directional signs
Place sponsor signs
Set up registration station:
Stuff conference totes
Badges
Programs
Debrief Binder
Emergency Kit
Set up Quiet Room
Set up Speaker Lounge
Set up Staff/Volunteer Hospitality Room
Welcome speakers arriving today:
| 4:45 | Speaker #1 pickup at airport
| 5:30 | Speaker #2 approximate arrival
(name) to join Speaker #1 and #2 for dinner (time, place)
Dinner break for team at (time, place)
DAY ONE | WEDNESDAY
| 6:30 a.m. | Confirm Final Presentation Room Setups
|  | Details confirmed by (name) | Room 301
A/V is on and working
Presentations for each session is installed on laptop and working
Room is Configured Correctly
Daily agenda sign posted by door
Introductions for each session are on lectern
Handouts for each presenter are labeled and on front table
|  | Details confirmed by (name) | Room 308
A/V is on and working
Presentations for each session is installed on laptop and working
Room is Configured Correctly
Daily agenda sign is posted by door
Introductions for each session are on lectern
Handouts for each presenter are labeled and on front table
| 7:00 | Registration Table Open
Staff assignments:
#1 (name)
#2 (name)
#3 (name)
| 7:00 - 8:00 | Breakfast
Welcome given by (name)
Hospitality Announcements by (name)
| 8:00 | Speaker #1 greeted by (name)
| 8:00 | Speaker #2 greeted by (name)
| 8:15 | Conduct sound check | Room 301
| 8:15 | Conduct sound check | Room 308
| 8:30 - 9:30 | Session 1
|  | Track 1 - “Tips and Tricks for the Advanced User” - Speaker #1 | Room 301 |  | Special Needs: will use his own laptop, have IT staff on standby for testing
Introduced by (name)
Facilitator/Notetaker (name)
Handouts Y/N
|  | Track 2 - “Essentials for Beginners” - Speaker #2 | Room 308 |  | Special Needs: needs a lavalier microphone and a flipchart with markers
Introduced by (name)
Facilitator Notetaker (name)
Handouts Y/N
| 9:30 - 10:00 | Break
| 10:00 - 11:00 | Session 2
Continue creating this kind of detail for each activity throughout the day for each day of your event. Indicate miscellaneous items, for instance when a room needs to be reconfigured for a different activity or when and where sponsors need to gather in order to be introduced at lunch.
FINAL DAY/TEARDOWN |  | Teardown
| 11:00 | Tear down Staff/Volunteer Hospitality Room
| 11:00 - 2:00 | Exhibitor teardown
| 11:00 | Box up directional signs
| 11:00 | Box up sponsor signs
| 1:00 | Tear down registration station
| 1:00 | Tear down Quiet Room
| 1:00 | Tear down Speaker Lounge
| 1:00 | A/V teardown begins
Remove all trash to appropriate location
Ship boxes back to headquarters
Final walkthrough of all event spaces
Touch base with venue representatives before departing
Relax and celebrate a job well done!