## Sheet1
ACTION PLAN The action steps listed on this worksheet will be used to make your vision a reality. Add as much detail as you need to paint a clear picture of what needs to be done, identify who is responsible for completing each task, set a target date, and record the actual completion date for each item. If you see that completion dates are starting to lag from the target dates that were originally set for the task, you are off schedule; you must evaluate whether you need to adjust the scope of the plan in order to avoid a critical misstep as you approach your event date. Use a spreadsheet or other tool that you can sort by column to quickly sort the list by target date, completed date, or responsible party. Add other columns to help you see your plan in a way that makes sense to you. For instance, add a “Category” or “Team” column so you can easily see what needs to be discussed with each team at your next progress meeting. Add an “Urgency” column so you can indicate whether the task is a critical path item that requires completion before other tasks can begin. The scenario below assumes that you have twelve months to plan your event. If your planning window is shorter, you will have to adjust your action plan accordingly. The example is a high level list of action items; each item would most likely have many lines underneath it with each step necessary to complete that particular action and a person assigned to each step. The day-of activities will be added to the more detailed Event Script.
| ACTION ITEM | DETAILS | WHO | TARGET DATE | COMPLETED DATE
12 MONTHS PRIOR | Identify Goals
Prepare Budget
Venue - send RFP's
Venue - site visits
Venue - evaluate proposals
Venue - negotiate and sign contract
Venue - pay deposit if necessary
Form a core team
Confirm event date
Create a theme
Create an invite list or target market
Send out Save The Date announcements
Create and launch marketing plan
Select a registration method
Launch event website
Launch call for speakers
Launch sponsorship campaign
Sponsors - collect logos, etc.
Conduct initial planning meeting
Create a schedule of planning meetings
Publish planning meeting schedule to team
Conduct a risk assessment and add necessary action items
6 MONTHS PRIOR | Secure keynotes, speakers
Secure vendors - equipment rentals
Secure vendors - technology
Secure vendors - audio/visual
Secure vendors - catering
Secure vendors - security
Inform venue of third party vendors
Secure entertainers
Secure after-hours activity
Finalize event agenda
Create hour-by-hour script
Set deadline and pricing structure
Launch participant registration
Launch exhibitor registration
Secure additional staff and volunteers
Secure all necessary transportation
Prepare sleeping room reservation list for staff and volunteers
Monitor registration pace and continue marketing campaign
Continue to solicit sponsorships
Continue to update event website with sessions, speakers, activities and sponsor details as they become known
3 MONTHS PRIOR | Secure badge printing supplies
Secure staff and volunteer clothing
Continue marketing campaign
Reminders published regarding early bird deadline
Collect speaker bios, headshots, presentations, handouts, etc.
Continue to update event website with new sessions speakers, activities, and sponsor details
Order conference totes and other giveaway items
Provide master schedule of events to venue
2 MONTHS PRIOR | Reminders published regarding regular registration deadline
Finalize menu and provide to menu
Begin to prepare printed conference program
30 DAYS PRIOR | Final marketing push for late registrations
Confirm detailed banquet event orders with venue
Secure remaining speaker bios, headshots, presentations, handouts, etc.
Deliver final conference program to printer
Prepare copies of all handouts, signage, speaker lists, maps, and other printed collateral
Prepare speaker introductions and identify facilitators who will introduce them
2 WEEKS PRIOR | Send to participants - last minute reminders
Send to participants - schedule changes
Send to participants - check-in instructions
Send to participants - directions and hotel information
Send to participants - list of what they should bring (and what they should leave at home )
Send final details to exhibitors including arrival and setup times
1 WEEK PRIOR | Confirm speakers and presenters
Confirm vendors and service providers
Confirm tracking and delivery estimates for shipped items
Review transportation, traffic, and parking arrangements
Confirm final meal counts to venue
Gather and/or ship - signs
Gather and/or ship - centerpieces, décor
Gather and/or ship - handouts
Gather and/or ship - emergency kit
Gather and/or ship - team supplies (badges, parking passes, etc.)
Organize contracts
Organize copies of banquet event orders
Organize emergency contacts
Organize attendance and exhibitor lists
Organize speaker introductions
Organize thank you notes and payments
Prepare event script
Finalize participant programs
Finalize conference totes and contents
Finalize swag and promotional items
Finalize badges and printing supplies
Team - confirm arrival times and initial tasks
Team - distribute event script
Team - review emergency procedures
Team - answer questions
Team - thank them for their efforts
DAY BEFORE | Travel to event site
Pre-con meeting with event staff to review BEO's and other final details
Setup - load-in procedures
Setup - exhibitor setup
Setup - A/V and technology
Setup - sign placement
Setup - registration station setup
Complete walk-through of all spaces
Welcome arriving guests, speakers, VIP's
Arrange meal and breaks for team members
AFTER THE EVENT | Tear down signs and displays
Box and label items for transport or shipping
Initiate survey to participants
Initiate survey to exhibitors
Thank yous - presenters
Thank yous - vendors
Thank yous - sponsors
Thank yous - service providers
Thank yous - participants
Reconcile revenue
Reconcile final venue invoice
Reconcile other expenses
Bank reconciliation
Prepare financial and other reports